## Initial Plan
Color Coding |  | Completed |  |  |  | SPRING 2023 SEMESTER
In Progress
[5 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
[5 empty] | Date | 2023-01-17 | 2023-01-24 | 2023-01-31 | 2023-02-07 | 2023-02-14 | 2023-02-21 | 2023-02-28 | 2023-03-07 | 2023-03-14 | 2023-03-21 | 2023-03-28 | 2023-04-04 | 2023-04-11 | 2023-04-18 | 2023-04-25 | 2023-05-02 | 2023-05-09
Project Phase | Activity | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals | ALL | 2023-01-17 | 2023-01-24 | 100%
| Confirm Project Team Roles | ALL | 2023-01-24 | 2023-01-31 | 100%
| Develop two business cases | Prathima SR, Akshat Shanbhag | 2023-01-31 | 2018-02-07 | 100%
| Develop Project Initiation Document (PID) | Prathima SR | 2023-02-07 | 2023-02-14 | 100%
| Produce initial Project Plan, RACI | Prathima SR | 2023-02-07 | 2023-02-14 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles | Daulet Kapezov | 2023-02-14 | 2023-02-21 | 100%
| Produce Context Diagram, Define System Interfaces | Rahul Mendes | 2023-02-14 | 2023-02-21 | 100%
| Define Business Requirements | Daulet Kapezov | 2023-02-14 | 2023-02-21 | 100%
| Agree to System Requirements types | All | 2023-02-14 | 2023-02-21 | 100%
| Define Functional Decomposition | Rahul Mendes | 2023-02-21 | 2023-02-28 | 100%
| Produce Rough Sketch of Home Page Design | Prathima S R | 2023-02-21 | 2023-02-21 | 100%
| Produce RCT document | Rahul Mendes | 2023-02-21 | 2023-02-28 | 100%
| Update Project Plan with additional requirements tasks | Prathima SR | 2023-02-28 | 2023-03-07 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) | Kritika Agarwal/ Ajay Peduri | 2023-02-28 | 2023-03-07 | 100%
| Database Design (ERD, Table spec) | Shubham Mishra | 2023-02-28 | 2023-03-07 | 100%
| System Interface Design | Kritika Agarwal/ Ajay Peduri | 2023-03-07 | 2023-03-28 | 100%
| User interface design | Kritika Agarwal/ Ajay Peduri | 2023-03-07 | 2023-03-28 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | GUI & Functionality Detailed Design | ALL | 2023-03-28 | 2023-04-04 | 100%
| Establish code repository in GitHUb | ALL | 2023-03-28 | 2023-04-04 | 100%
| Field Validation Crosscut Implementation in the UI fields | ALL | 2023-04-04 | 2023-04-11 | 100%
| Perform calculations to integrate the UI and Backend | ALL | 2023-04-04 | 2023-04-11 | 100%
| Design UI Page for Register Landlord & Renter | ALL | 2023-04-04 | 2023-04-11 | 100%
| Design UI Page for Modification of Landlord & Renter | ALL | 2023-04-11 | 2023-04-18 | 100%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document | Akshat Shanbhag/ Dhruv Chamaria | 2023-04-18 | 2023-04-25 | 100%
| Evaluate Features to be Tested | Akshat Shanbhag/ Dhruv Chamaria | 2023-04-18 | 2023-04-25 | 100%
| Design Test Cases | Akshat Shanbhag/ Dhruv Chamaria | 2023-04-25 | 2023-05-09 | 100%
| Execute Test Cases | Akshat Shanbhag/ Dhruv Chamaria | 2023-04-25 | 2023-05-09 | 100%
| Anaylze Test Results | ALL | 2023-04-25 | 2023-05-09 | 100%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation | ALL | 2023-05-09 | 2023-05-15 | 100%