## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 01. Searching | 1.01 | 01.01 Search by ZIP | Include a text input field for users to enter the ZIP code | 2023-09-29 | 2023-10-02 | 100% | Prathima
2 | 01. Searching | 1.01 | 01.01 Search by ZIP | Add a search button or trigger mechanism | 2023-09-29 | 2023-10-02 | 100% | Prathima
3 | 01. Searching | 1.01 | 01.01 Search by ZIP | Set up an event listener on the search button | 2023-09-29 | 2023-10-02 | 100% | Prathima
4 | 01. Searching | 1.01 | 01.01 Search by ZIP | Formulate a database query to retrieve houses or properties based on the given ZIP code | 2023-09-29 | 2023-10-02 | 100% | Prathima
5 | 01. Searching | 1.01 | 01.01 Search by ZIP | Update the UI to show the results returned by the backend | 2023-09-29 | 2023-10-02 | 100% | Prathima
6 | 01. Searching | 1.01 | 01.01 Search by ZIP | Develop test cases for Search by ZIP functionality | 2023-09-29 | 2023-10-02 | 100% | Dhruv Chamaria
7 | 01. Searching | 1.01 | 01.01 Search by ZIP | Execute test cases listed for Search by ZIP functionality | 2023-09-29 | 2023-10-02 | 100% | Ajay
8 | 01. Searching | 1.02 | 01.02 Search by City | Include a text input field for users to enter the City name | 2023-10-02 | 2023-10-05 | 100% | Shubham
9 | 01. Searching | 1.02 | 01.02 Search by City | Implement client-side validation for the city name input | 2023-10-02 | 2023-10-06 | 100% | Kritika
10 | 01. Searching | 1.02 | 01.02 Search by City | Set up an event listener on the search button | 2023-10-02 | 2023-10-06 | 100% | Shubham
11 | 01. Searching | 1.02 | 01.02 Search by City | Retrieve the city name from the input field | 2023-10-02 | 2023-10-06 | 100% | Rahul Mendes
12 | 01. Searching | 1.02 | 01.02 Search by City | Use AJAX or a modern alternative to make asynchronous requests to the backend | 2023-10-02 | 2023-10-06 | 100% | Prathima
13 | 01. Searching | 1.02 | 01.02 Search by City | Create a new API endpoint to handle city searches | 2023-10-02 | 2023-10-06 | 100% | Kritika
14 | 01. Searching | 1.02 | 01.02 Search by City | Formulate a database query to retrieve houses or properties based on the given city | 2023-10-02 | 2023-10-06 | 100% | Shubham
15 | 01. Searching | 1.02 | 01.02 Search by City | Send a well-structured response, preferably in JSON format | 2023-10-02 | 2023-10-06 | 100% | Akshat
16 | 01. Searching | 1.02 | 01.02 Search by City | Update the UI to show the results returned by the backend | 2023-10-02 | 2023-10-06 | 100% | Daulet
17 | 01. Searching | 1.02 | 01.02 Search by City | Develop test cases for Search by City functionality | 2023-10-02 | 2023-10-06 | 100% | Dhruv Chamaria
18 | 01. Searching | 1.02 | 01.02 Search by City | Execute test cases listed for Search by City functionality | 2023-10-02 | 2023-10-06 | 100% | Ajay
19 | 01. Searching | 1.04 | 01.04 Sort by Price | Include a dropdown or buttons for selecting the sorting option (ascending or descending) | 2023-10-06 | 2023-10-11 | 100% | Ajay
20 | 01. Searching | 1.04 | 01.04 Sort by Price | Implement UI components for users to interact with, such as buttons or a dropdown menu for selecting sorting options | 2023-10-06 | 2023-10-11 | 100% | Prathima
21 | 01. Searching | 1.04 | 01.04 Sort by Price | Set up event listeners for the sorting options to trigger the sorting functionality | 2023-10-06 | 2023-10-11 | 100% | Kritika
22 | 01. Searching | 1.04 | 01.04 Sort by Price | Create or modify an existing API endpoint to handle sorting by price | 2023-10-06 | 2023-10-11 | 100% | Kritika
23 | 01. Searching | 1.04 | 01.04 Sort by Price | Retrieve data from the database based on the sorting criteria and fetch relevant information such as address, price, and availability. | 2023-10-06 | 2023-10-11 | 100% | Shubham
24 | 01. Searching | 1.04 | 01.04 Sort by Price | Process the data retrieved from the database, format it as needed | 2023-10-06 | 2023-10-11 | 100% | Shubham
25 | 01. Searching | 1.04 | 01.04 Sort by Price | Send a well-structured response, preferably in JSON format, with the sorted data and include relevant details about the houses sorted by price | 2023-10-06 | 2023-10-12 | 100% | Prathima
26 | 01. Searching | 1.04 | 01.04 Sort by Price | Develop test cases for Sort by Price functionality | 2023-10-06 | 2023-10-12 | 100% | Dhruv Chamaria
27 | 01. Searching | 1.04 | 01.04 Sort by Price | Execute test cases listed for Sort by Price functionality | 2023-10-06 | 2023-10-12 | 100% | Ajay
28 | 03. Account Management | 3.05 | 03.05 Deactivate Renter | Design a user interface that includes options for managing renters, including a "Deactivate Renter" button or similar | 2023-10-10 | 2023-10-12 | 100% | Rahul Mendes
29 | 03. Account Management | 3.05 | 03.05 Deactivate Renter | Implement UI components for users to interact with, such as buttons or links for deactivating renters | 2023-10-10 | 2023-10-12 | 100% | Daulet
30 | 03. Account Management | 3.05 | 03.05 Deactivate Renter | Implement a confirmation modal or dialog to confirm the deactivation action. | 2023-10-10 | 2023-10-12 | 100% | Daulet
31 | 03. Account Management | 3.05 | 03.05 Deactivate Renter | Include a message explaining the consequences of deactivation | 2023-10-10 | 2023-10-12 | 100% | Daulet
32 | 03. Account Management | 3.05 | 03.05 Deactivate Renter | Set up event listeners for the "Deactivate Renter" button or link to trigger the deactivation process. | 2023-10-10 | 2023-10-12 | 100% | Ajay
33 | 03. Account Management | 3.05 | 03.05 Deactivate Renter | Create a new API endpoint or modify an existing one to handle renter deactivation. | 2023-10-10 | 2023-10-12 | 100% | Kritika
34 | 03. Account Management | 3.05 | 03.05 Deactivate Renter | Update the database to mark the renter as deactivated | 2023-10-10 | 2023-10-12 | 10% | Shubham
35 | 03. Account Management | 3.05 | 03.05 Deactivate Renter | Send a well-structured response, preferably in JSON format, indicating the success or failure of the deactivation process. | 2023-10-10 | 2023-10-12 | 100% | Prathima
36 | 03. Account Management | 3.05 | 03.05 Deactivate Renter | Develop test cases for Deactivate renter functionality | 2023-10-12 | 2023-10-13 | 100% | Dhruv Chamaria
37 | 03. Account Management | 3.05 | 03.05 Deactivate Renter | Execute test cases listed for Deactivate renter functionality | 2023-10-12 | 2023-10-13 | 100% | Ajay

## I2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 02. Property Listing | 2.01 | 02.01 List Various Properties | Create Property Listing Page | 2023-10-15 | 2023-10-18 | 100% | Prathima
2 | 02. Property Listing | 2.01 | 02.01 List Various Properties | Implement Filters | 2023-10-15 | 2023-10-18 | 100% | Shubham
3 | 02. Property Listing | 2.01 | 02.01 List Various Properties | Property Detail Page | 2023-10-15 | 2023-10-18 | 100% | Rahul
4 | 02. Property Listing | 2.01 | 02.01 List Various Properties | Map Integration | 2023-10-15 | 2023-10-18 | 100% | Kritika
5 | 02. Property Listing | 2.01 | 02.01 List Various Properties | Search Functionality | 2023-10-15 | 2023-10-18 | 100% | Akshat
6 | 02. Property Listing | 2.01 | 02.01 List Various Properties | Database Schema | 2023-10-15 | 2023-10-18 | 100% | Shubham
7 | 02. Property Listing | 2.01 | 02.01 List Various Properties | API Endpoints | 2023-10-15 | 2023-10-18 | 100% | Kritika
8 | 02. Property Listing | 2.01 | 02.01 List Various Properties | Business Logic | 2023-10-15 | 2023-10-18 | 100% | Dhruv
9 | 02. Property Listing | 2.01 | 02.01 List Various Properties | Security | 2023-10-15 | 2023-10-18 | 100% | Ajay
10 | 02. Property Listing | 2.01 | 02.01 List Various Properties | Develop test cases | 2023-10-15 | 2023-10-18 | 100% | Dhruv
11 | 02. Property Listing | 2.01 | 02.01 List Various Properties | Execute test cases | 2023-10-15 | 2023-10-18 | 100% | Ajay
12 | 02. Property Listing | 2.02 | 02.02 Add Amenities | Create Amenities Form | 2023-10-18 | 2023-10-22 | 100% | Prathima
13 | 02. Property Listing | 2.02 | 02.02 Add Amenities | Design Amenity Card Component | 2023-10-18 | 2023-10-22 | 100% | Prathima
14 | 02. Property Listing | 2.02 | 02.02 Add Amenities | Implement User Notifications | 2023-10-18 | 2023-10-22 | 100% | Dhruv
15 | 02. Property Listing | 2.02 | 02.02 Add Amenities | Make a Database Schema | 2023-10-18 | 2023-10-22 | 100% | Shubham
16 | 02. Property Listing | 2.02 | 02.02 Add Amenities | Create API Endpoints | 2023-10-18 | 2023-10-22 | 100% | Kritika
17 | 02. Property Listing | 2.02 | 02.02 Add Amenities | Develop test cases | 2023-10-18 | 2023-10-22 | 100% | Dhruv
18 | 02. Property Listing | 2.02 | 02.02 Add Amenities | Execute test cases | 2023-10-18 | 2023-10-22 | 100% | Ajay
19 | 02. Property Listing | 2.03 | 02.03 Add Surrounding Areas | Display Surrounding Areas | 2023-10-22 | 2023-10-27 | 100% | Prathima
20 | 02. Property Listing | 2.03 | 02.03 Add Surrounding Areas | Surrounding Area Card Component | 2023-10-22 | 2023-10-27 | 100% | Akshat
21 | 02. Property Listing | 2.03 | 02.03 Add Surrounding Areas | User Notifications | 2023-10-22 | 2023-10-27 | 100% | Prathima
22 | 02. Property Listing | 2.03 | 02.03 Add Surrounding Areas | Surrounding Area Validation | 2023-10-22 | 2023-10-27 | 100% | Daulet
23 | 02. Property Listing | 2.03 | 02.03 Add Surrounding Areas | Authorization of areas | 2023-10-22 | 2023-10-27 | 100% | Daulet
24 | 02. Property Listing | 2.03 | 02.03 Add Surrounding Areas | Develop test cases | 2023-10-22 | 2023-10-27 | 100% | Dhruv
25 | 02. Property Listing | 2.03 | 02.03 Add Surrounding Areas | Execute test cases | 2023-10-22 | 2023-10-27 | 100% | Ajay
26 | 02. Property Listing | 2.04 | 02.04 Display Verified Property | Make a UI Design | 2023-10-27 | 2023-11-03 | 100% | Prathima
27 | 02. Property Listing | 2.04 | 02.04 Display Verified Property | Filter for Verified Properties | 2023-10-27 | 2023-11-03 | 100% | Shubham
28 | 02. Property Listing | 2.04 | 02.04 Display Verified Property | Display Verification Details | 2023-10-27 | 2023-11-03 | 100% | Daulet
29 | 02. Property Listing | 2.04 | 02.04 Display Verified Property | create API Endpoints | 2023-10-27 | 2023-11-03 | 100% | Kritika
30 | 02. Property Listing | 2.04 | 02.04 Display Verified Property | Implement Verification Logic | 2023-10-27 | 2023-11-03 | 100% | Daulet
31 | 02. Property Listing | 2.04 | 02.04 Display Verified Property | Develop test cases | 2023-10-27 | 2023-11-03 | 100% | Dhruv
32 | 02. Property Listing | 2.04 | 02.04 Display Verified Property | Execute test cases | 2023-10-27 | 2023-11-03 | 100% | Ajay