## Road Map
Stay Match Application
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 10/13/22 | Iteration 2 - 11/04/22 | Iteration 3 - 11/17/22 | Iteration 4 - 12/15/22
Module 1 - Search | 01.01 Search by City | 5 | x
| 01.02 Search vy ZIP | 5 | x
| 01.03 Search by Criteria | 4 |  |  | x
| 01.04 Sort by Price | 2 | x
Module 2 - Property Listing | 02.01 List Various Properties | 3 |  | x
| 02.02 Add Amenities | 3 |  | x
| 02.03 Add Surrounding areas | 3 |  | x
| 02.04 Display verified property | 2 |  | x
Module 3 - Account Management | 03.01 Register Renter | [5 empty] | Features implemented last sem
03.02 Modify Renter
03.03 Register Landlord
03.04 Modify Landlord
| 03.05 Deactivate Renter | 2 | x
Module 4 - Property Management | 04.01 Add a Property | 4 |  |  | x
| 04.02 Update a Property | 2 |  |  | x
| 04.03 Delete a Property | 3 |  |  |  | x
| 04.04 Show Property Summary | 2 |  |  |  | x
| 04.05 Show Contact Information | 4 |  |  | x
Module 5 - Property Validation | 05.01 Validate Address | 3 |  |  |  | x
| 05.02 Validate Contact Information | 2 |  |  |  | x
|  | VELOCITY: | 14 | 11 | 14 | 10

## Story Map
Epics |  | QuickFeed - User Story Map
Epic 1 - Search |  | Epic 1 - Search | Epic 2 - Categories | Epic 3 - Account Management | Epic 4 - Suggestions
Epic 2 - Categories | User Stories | 01.04 Summarize the details | 02.01 Access the list of service providers | 3.05 Create and Modify the Account |  | Iteration 1
Epic 3 - Account Management |  | 01.01 Search by a User | 2.02 Filter the list of Goods/ service providers
Epic 4 - Suggestions |  | 01.02 Search for a Goods/Service Provider |  |  |  | Iteration 2
04.01 Display the relevant Ratings
[5 empty] | 4.02 Display the top rated Reviews | Iteration 3
|  | 01.03 Optimize the search |  | 3.03 Contact the customer support |  | Iteration 4