## R2 I3
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R2 - I3 | 01. Searching | 1.3 | 01.03 Search by Criteria | UI Design: Collaborate with designers to create a user-friendly interface for the search | 2023-11-04 | 2023-11-08 | 100% | Prathima
2 | R2 - I3 | 01. Searching | 1.3 | 01.03 Search by Criteria | Implement client-side input validation | 2023-11-04 | 2023-11-09 | 100% | Prathima
3 | R2 - I3 | 01. Searching | 1.3 | 01.03 Search by Criteria | Develop the search form with input fields for various criter | 2023-11-04 | 2023-11-10 | 100% | Kritika
4 | R2 - I3 | 01. Searching | 1.3 | 01.03 Search by Criteria | Design and implement a results display | 2023-11-04 | 2023-11-10 | 100% | Shubham
5 | R2 - I3 | 01. Searching | 1.3 | 01.03 Search by Criteria | Create error-handling mechanisms | 2023-11-04 | 2023-11-10 | 100% | Akshat
6 | R2 - I3 | 01. Searching | 1.3 | 01.03 Search by Criteria | Define API endpoints and request parameters for the search | 2023-11-04 | 2023-11-10 | 100% | Kritika
7 | R2 - I3 | 01. Searching | 1.3 | 01.03 Search by Criteria | Implement server-side input validation | 2023-11-04 | 2023-11-10 | 100% | Rahul
8 | R2 - I3 | 01. Searching | 1.3 | 01.03 Search by Criteria | Write queries to retrieve data from the database | 2023-11-04 | 2023-11-10 | 100% | Shubham
9 | R2 - I3 | 01. Searching | 1.3 | 01.03 Search by Criteria | Optimize database queries to ensure fast retrieval | 2023-11-04 | 2023-11-10 | 100% | Shubham
10 | R2 - I3 | 01. Searching | 1.3 | 01.03 Search by Criteria | Design Test cases for the Search by Criteria feature | 2023-11-04 | 2023-11-10 | 100% | Dhruv
11 | R2 - I3 | 04. Property Management | 4.5 | 04.05 Show Contact Info | Execute the test cases for the Search by Criteria Feature | 2023-11-10 | 2023-11-15 | 100% | Ajay
12 | R2 - I3 | 04. Property Management | 4.5 | 04.05 Show Contact Info | Collaborate with designers to create an intuitive and user-friendly interface | 2023-11-10 | 2023-11-17 | 100% | Prathima
13 | R2 - I3 | 04. Property Management | 4.5 | 04.05 Show Contact Info | Implement access controls to ensure that only authorized users can view contact information. | 2023-11-10 | 2023-11-17 | 100% | Rahul
14 | R2 - I3 | 04. Property Management | 4.5 | 04.05 Show Contact Info | Design the UI to trigger the "Show Contact Info" action | 2023-11-10 | 2023-11-17 | 100% | Daulet
15 | R2 - I3 | 04. Property Management | 4.5 | 04.05 Show Contact Info | Develop a section of the UI where the contact information will be displayed | 2023-11-10 | 2023-11-17 | 100% | Akshat
16 | R2 - I3 | 04. Property Management | 4.5 | 04.05 Show Contact Info | Implement authorization checks to ensure that the user has the necessary permissions | 2023-11-10 | 2023-11-17 | 100% | Akshat
17 | R2 - I3 | 04. Property Management | 4.5 | 04.05 Show Contact Info | Store contact information securely in the database. | 2023-11-10 | 2023-11-17 | 100% | Shubham
18 | R2 - I3 | 04. Property Management | 4.5 | 04.05 Show Contact Info | Configure database access controls | 2023-11-10 | 2023-11-17 | 100% | Shubham
19 | R2 - I3 | 04. Property Management | 4.5 | 04.05 Show Contact Info | Design Test cases for the Show Contact Info Feature | 2023-11-10 | 2023-11-17 | 100% | Dhruv
20 | R2 - I3 | 04. Property Management | 4.5 | 04.05 Show Contact Info | Execute the test cases for the Show Contact Info Feature | 2023-11-10 | 2023-11-17 | 100% | Ajay
21 | R2 - I3 | 04. Property Management | 4.1 | 04.01 Add Property | Design user-friendly and responsive UI for the "Add a Property" form | 2023-11-10 | 2023-11-17 | 100% | Prathima
22 | R2 - I3 | 04. Property Management | 4.1 | 04.01 Add Property | Implement client-side validation for fields | 2023-11-10 | 2023-11-17 | 100% | Shubham
23 | R2 - I3 | 04. Property Management | 4.1 | 04.01 Add Property | Implement submission of the property listing to the backend | 2023-11-10 | 2023-11-17 | 100% | Rahul
24 | R2 - I3 | 04. Property Management | 4.1 | 04.01 Add Property | Define the database schema for storing property information | 2023-11-10 | 2023-11-17 | 100% | Kritika
25 | R2 - I3 | 04. Property Management | 4.1 | 04.01 Add Property | Create API endpoints to handle property creation and submission | 2023-11-10 | 2023-11-17 | 100% | Daulet
26 | R2 - I3 | 04. Property Management | 4.1 | 04.01 Add Property | Design Test cases for the Add a Property Feature | 2023-11-10 | 2023-11-17 | 100% | Dhruv
27 | R2 - I3 | 04. Property Management | 4.1 | 04.01 Add Property | Execute the test cases for the Add a Property Feature | 2023-11-10 | 2023-11-17 | 100% | Ajay
28 | R2 - I3 | 04. Property Management | 4.2 | 04.02 Update Property | Fetch the existing property details from the backend | 2023-11-10 | 2023-11-17 | 100% | Kritika
29 | R2 - I3 | 04. Property Management | 4.2 | 04.02 Update Property | Allow users to edit or upload additional images for the property | 2023-11-10 | 2023-11-17 | 100% | Prathima
30 | R2 - I3 | 04. Property Management | 4.2 | 04.02 Update Property | Retrieve the existing property details from the database for editing | 2023-11-10 | 2023-11-17 | 100% | Rahul
31 | R2 - I3 | 04. Property Management | 4.2 | 04.02 Update Property | Validate incoming data to ensure it meets the required format | 2023-11-10 | 2023-11-17 | 100% | Akshat
32 | R2 - I3 | 04. Property Management | 4.2 | 04.02 Update Property | Design Test cases for the Add a Property Feature | 2023-11-10 | 2023-11-17 | 100% | Dhruv
33 | R2 - I3 | 04. Property Management | 4.2 | 04.02 Update Property | Execute the test cases for the Add a Property Feature | 2023-11-10 | 2023-11-17 | 100% | Ajay

## R2 I4
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R2 - I3 | 01. Searching | 4.3 | 04.03 Delete Property | Add a "Delete" button or option in the property details page. | 2023-11-23 | 2023-11-28 | 100% | Prathima
2 | R2 - I3 | 01. Searching | 4.3 | 04.03 Delete Property | Implement a confirmation modal to ensure the user intends to delete the property. | 2023-11-23 | 2023-11-28 | 100% | Prathima
3 | R2 - I3 | 01. Searching | 4.3 | 04.03 Delete Property | Handle user interactions and trigger the delete request. | 2023-11-23 | 2023-11-28 | 100% | Kritika
4 | R2 - I3 | 01. Searching | 4.3 | 04.03 Delete Property | Display user-friendly error messages in case of failures. | 2023-11-23 | 2023-11-28 | 100% | Shubham
5 | R2 - I3 | 01. Searching | 4.3 | 04.03 Delete Property | Provide feedback to the user after successful deletion. | 2023-11-23 | 2023-11-28 | 100% | Akshat
6 | R2 - I3 | 01. Searching | 4.3 | 04.03 Delete Property | Create a new API endpoint for handling property deletion requests. | 2023-11-23 | 2023-11-28 | 100% | Kritika
7 | R2 - I3 | 01. Searching | 4.3 | 04.03 Delete Property | Define the necessary request parameters (e.g., property ID). | 2023-11-23 | 2023-11-28 | 100% | Rahul
8 | R2 - I3 | 01. Searching | 4.3 | 04.03 Delete Property | Verify the user's identity and permissions before processing the delete request. | 2023-11-23 | 2023-11-28 | 100% | Shubham
9 | R2 - I3 | 01. Searching | 4.3 | 04.03 Delete Property | Ensure that the database schema allows for the deletion of properties. | 2023-11-23 | 2023-11-28 | 100% | Shubham
10 | R2 - I3 | 01. Searching | 4.3 | 04.03 Delete Property | Add test cases for Delete a Property feature | 2023-11-23 | 2023-11-28 | 100% | Dhruv
11 | R2 - I3 | 04. Property Management | 4.3 | 04.03 Delete Property | Execute test cases for Delete a Property feature | 2023-11-23 | 2023-11-28 | 100% | Ajay
12 | R2 - I3 | 04. Property Management | 4.4 | 04.04 Show Property Summary | Design and implement a UI component to display the summary of a property. | 2023-11-28 | 2023-12-02 | 100% | Prathima
13 | R2 - I3 | 04. Property Management | 4.4 | 04.04 Show Property Summary | Implement loading indicator | 2023-11-28 | 2023-12-02 | 100% | Rahul
14 | R2 - I3 | 04. Property Management | 4.4 | 04.04 Show Property Summary | Display user-friendly error messages in case of API request failures. | 2023-11-28 | 2023-12-02 | 100% | Daulet
15 | R2 - I3 | 04. Property Management | 4.4 | 04.04 Show Property Summary | Create a new API endpoint to retrieve property summary data. | 2023-11-28 | 2023-12-02 | 100% | Akshat
16 | R2 - I3 | 04. Property Management | 4.4 | 04.04 Show Property Summary | Write a query to fetch the relevant property summary data from the database. | 2023-11-28 | 2023-12-02 | 100% | Akshat
17 | R2 - I3 | 04. Property Management | 4.4 | 04.04 Show Property Summary | Ensure that the database schema supports the retrieval of property summary data efficiently. | 2023-11-28 | 2023-12-02 | 100% | Shubham
18 | R2 - I3 | 04. Property Management | 4.4 | 04.04 Show Property Summary | Add test cases for Show Property Summary feature | 2023-11-28 | 2023-12-02 | 100% | Dhruv
19 | R2 - I3 | 04. Property Management | 4.4 | 04.04 Show Property Summary | Execute test cases for Show Property Summary feature | 2023-11-28 | 2023-12-02 | 100% | Ajay
20 | R2 - I3 | 04. Property Management | 5.1 | 05.01 Validate Address | Design and implement a UI component that allows users to input and edit addresses. | 2023-12-02 | 2023-12-05 | 100% | Ajay
21 | R2 - I3 | 04. Property Management | 5.1 | 05.01 Validate Address | Include form validation to ensure users enter necessary address details. | 2023-12-02 | 2023-12-05 | 100% | Prathima
22 | R2 - I3 | 04. Property Management | 5.1 | 05.01 Validate Address | Implement real-time validation to provide immediate feedback to user | 2023-12-02 | 2023-12-05 | 100% | Shubham
23 | R2 - I3 | 04. Property Management | 5.1 | 05.01 Validate Address | Create an API endpoint to receive address validation requests. | 2023-12-02 | 2023-12-05 | 100% | Rahul
24 | R2 - I3 | 04. Property Management | 5.1 | 05.01 Validate Address | Sanitize and validate the input data received from the frontend to prevent vulnerabilities. | 2023-12-02 | 2023-12-05 | 100% | Kritika
25 | R2 - I3 | 04. Property Management | 5.1 | 05.01 Validate Address | Decide whether to store validated addresses in the database for future use. | 2023-12-02 | 2023-12-05 | 100% | Daulet
26 | R2 - I3 | 04. Property Management | 5.1 | 05.01 Validate Address | Add test cases for Validate Address feature | 2023-12-02 | 2023-12-05 | 100% | Dhruv
27 | R2 - I3 | 04. Property Management | 5.1 | 05.01 Validate Address | Execute test cases for Validate Address feature | 2023-12-02 | 2023-12-05 | 100% | Ajay
28 | R2 - I3 | 04. Property Management | 5.2 | 05.02 Validate Contact Info | Design and implement a UI component that allows users to input and edit contact information. | 2023-12-05 | 2023-12-08 | 100% | Kritika
29 | R2 - I3 | 04. Property Management | 5.2 | 05.02 Validate Contact Info | Include form validation to ensure users enter valid contact information. | 2023-12-05 | 2023-12-08 | 100% | Prathima
30 | R2 - I3 | 04. Property Management | 5.2 | 05.02 Validate Contact Info | Display clear error messages if the entered contact information is invalid or incomplete. | 2023-12-05 | 2023-12-08 | 100% | Rahul
31 | R2 - I3 | 04. Property Management | 5.2 | 05.02 Validate Contact Info | Create an API endpoint to receive contact information validation requests. | 2023-12-05 | 2023-12-08 | 100% | Akshat
32 | R2 - I3 | 04. Property Management | 5.2 | 05.02 Validate Contact Info | Validate the input data received. | 2023-12-05 | 2023-12-08 | 100% | Dhruv
33 | R2 - I3 | 04. Property Management | 5.2 | 05.02 Validate Contact Info | Add test cases for Validate Contact Info feature | 2023-12-05 | 2023-12-08 | 100% | Dhruv
|  |  | 5.2 | 05.02 Validate Contact Info | Execute test cases for Validate Contact Info feature | 2023-12-05 | 2023-12-08 | 100% | Ajay